## Planned Burndown Chart
PLANNED BURNDOWN CHART
BACKLOG TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a Lab Manager/Head Researcher, I need the ability to manage all permissions in the system, so i can manage access to experiments #82 | 1
Lab Manager can alter permissions for co-researchers | 0.33
co-researchers can only access permitted pages | 0.33
an interface that allows this be done without having to access the database directly | 0.33
As a Head Researcher, I should have the ability to make a new questionnaires from the front-end so that I can gather both qualitative and quantative data #69 | 18
The ability to phrase questions for the participant to answer
The ability to add radio buttons.
the ability to add numbers and text
As a Lab Manager/Head Researcher, I need the ability to manage all other users in a system so that I can manage their accounts. #81 | 8
the ability to add researchers
the ability change passwords,
the ability to delete researchers
the ability to alter email addresses
the ability to change researcher's details
an interface that allows this be done without accessing the database directly
As a Co-Researcher, I should be able to view experiments I have been assigned to so that I can aid in the research. #60 | 2
Create a specific co researcher view
Creating a stored procedure which returns all the questionnaire which belongs to a particular co-researcher
Display all the questionnaire to which researcher they belong to
co-researcher can see their experiments
As a Principal Researcher, I should be able to view the results of my experiments. #59 | 5
Create A view
Display all the questionnaires and which researcher they belong to
Creating a stored procedure which returns all the questionnaires which belongs to a particular researcher
Researcher can see the results of their experiment
As Head Researcher, I need to be able to view individual responses to the questionnaire, so i can examine the data closely #34 | 2
Grab the questions from a participant’s response
And the answers from a participant’s response
Data Displayed in a readable format
As a Lab Manager/Head Researcher, I should be able to view all experiments so that I can analyse all of the data. #80 | 1
DB Procedure to show responses for specified questionnaire.
Head Researcher can view an experiment
Head Researcher can view all experiments
As a Head Researcher, I need to be able to export the data as a CSV file so that I can store the results locally on my computer. #8 | 2
create an export button
export button exports data
exported data can be read
As Head Researcher, I need a mandatory consent form to be completed before participants complete the questionnaire so that they are fully informed of what is expected of them. #1 | 2
create a page with the consent stuff and confirm button
It then redirect to the questionnaire if button pressed (maybe can be done for bootstrap or java).
TOTAL

## Actual Burndown Chart
ACTUAL BURNDOWN CHART
BACKLOG TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.